## Smart-Nest (hidden)
[8 empty] | SMART'2011 (kick-off meeting) | [12 empty] | SolMech'2012 | [5 empty] | ECL |  |  |  |  | SMART'2013 | [6 empty] | LZPQ, midterm | [6 empty] | IPPT |  |  |  |  | CEDRAT |  |  |  |  | SMART'2015 (Smart-Nest session) |  |  |  |  | IPPT PARIS (final meeting)
contract type (A-contract, B-stipend) | Ref in NEF | [Sending institution] [Country] [Commercial sector Y/N] | [Hosting/ Recruiting institution] [Country] [Commerial sector Y/N] | Active in WP | Type | Fellow starts at project month | Total PM | Year 0 2011 | [5 empty] | Year 1 2012 | [11 empty] | Year 2 2013 | [11 empty] | Year 3 2014 | [11 empty] | Year 4 2015
[8 empty] | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
[8 empty] | 0 | [5 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48
Start
A | 1 | [ADAPTRONICA], [PL], [Y] | [IPPT], [PL], [N] | 1-4,6,8 | ER2 | 25 | 11 | [30 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11
A | 2 | [ADAPTRONICA], [PL], [Y] | [ECL],[FR],[N] | 3,4,6,8 | ER2 | 37 | 6 | [42 empty] | 1 | 2 | 3 | 4 | 5 | 6
A | 3 | [ADAPTRONICA], [PL], [Y] | [ECL],[FR],[N] | 3,4,8 | ER1 | 25 | 4 | [30 empty] | 1 | 2 | 3 | 4
B | 4 | [IDEAL], [DE], [Y] | [ECL],[FR],[N] | 4-6,8 | ER1 | 18 | 4 | [23 empty] | 1 | 2 | 3 | 4
B | 5 | [IDEAL], [DE], [Y] | [ECL],[FR],[N] | 4-6,8 | ER1 | 38 | 4 | [43 empty] | 1 | 2 | 3 | 4
A | 6 | [ADAPTRONICA], [PL], [Y] | [LZPQ],[DE],[N] | 1-4,6,8 | ER2 | 25 | 6 | [30 empty] | 1 | 2 | 3 | 4 | 5 | 6
A | 7 | [ADAPTRONICA], [PL], [Y] | [LZPQ],[DE],[N] | 1-4,6,8 | ER2 | 19 | 6 | [24 empty] | 1 | 2 | 3 | 4 | 5 | 6
A | 8 | [IDEAL], [DE], [Y] | [LZPQ],[DE],[N] | 1,4-6,8 | ER2 | 7 | 9 | [12 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9
A | 9 | [IPPT], [PL], [N] | [ADAPTRONICA], [PL], [Y] | 1-3,6,8 | ER2 | 13 | 11 | [18 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11
B | 10 | [ECL],[FR],[N] | [ADAPTRONICA], [PL], [Y] | 3,4,8 | ESR | 6 | 4 | [11 empty] | 1 | 2 | 3 | 4
B | 11 | [ECL],[FR],[N] | [ADAPTRONICA], [PL], [Y] | 3,4,8 | ESR | 8 | 4 | [13 empty] | 1 | 2 | 3 | 4
A | 12 | [ECL],[FR],[N] | [ADAPTRONICA], [PL], [Y] | 3,4,6 | ER1 | 14 | 11 | [19 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11
B | 13 | [LZPQ],[DE],[N] | [ADAPTRONICA], [PL], [Y] | 1,2,4,5,8 | ESR | 10 | 4 | [15 empty] | 1 | 2 | 3 | 4
B | 14 | [LZPQ],[DE],[N] | [ADAPTRONICA], [PL], [Y] | 1,2,4,5,8 | ESR | 6 | 4 | [11 empty] | 1 | 2 | 3 | 4
A | 15 | [LZPQ],[DE],[N] | [ADAPTRONICA], [PL], [Y] | 1,2,4,5,8 | ER2 | 3 | 11 | [8 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11
B | 16 | [IPPT], [PL], [N] | [IDEAL], [DE], [Y] | 1-8 | ER2 | 14 | 1 | [19 empty] | 1
B | 17 | [IPPT], [PL], [N] | [CEDRAT], [FR], [Y] | 4,5,8 | ER2 | 14 | 4 | [19 empty] | 1 | 2 | 3 | 4
B | 18 | [IPPT], [PL], [N] | [CEDRAT], [FR], [Y] | 4-6,8 | ER2 | 27 | 3 | [32 empty] | 1 | 2 | 3
B | 19 | [IPPT], [PL], [N] | [CEDRAT], [FR], [Y] | 3-6,8 | ER2 | 37 | 3 | [42 empty] | 1 | 2 | 3
B | 20 | [IPPT], [PL], [N] | [CEDRAT], [FR], [Y] | 4,5,8 | ER1 | 14 | 4 | [19 empty] | 1 | 2 | 3 | 4
B | 21 | [ECL],[FR],[N] | [CEDRAT], [FR], [Y] | 4-6,8 | ESR | 37 | 4 | [42 empty] | 1 | 2 | 3 | 4
A | 22 | [ECL],[FR],[N] | [CEDRAT], [FR], [Y] | 4,5,8 | ER1 | 25 | 12 | [30 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
B | 23 | [LZPQ],[DE],[N] | [CEDRAT], [FR], [Y] | 1,4-6,8 | ESR | 18 | 4 | [23 empty] | 1 | 2 | 3 | 4
A | 24 | [LZPQ],[DE],[N] | [CEDRAT], [FR], [Y] | 1,4-6,8 | ER1 | 15 | 12 | [20 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
B | 25 | [IPPT], [PL], [N] | [CEDRAT], [FR], [Y] | 1-8 | ER2 | 2 | 1 | [7 empty] | 1
B | 26 | [IPPT], [PL], [N] | [IDEAL], [DE], [Y] | 1,4-6,8 | ER2 | 30 | 3 | [35 empty] | 1 | 2 | 3
B | 27 | [IPPT], [PL], [N] | [IDEAL], [DE], [Y] | 1,4,5,8 | ER2 | 15 | 4 | [20 empty] | 1: 1; 2: 2; 3: 3; 1 4: 4
B | 28 | [IPPT], [PL], [N] | [IDEAL], [DE], [Y] | 1,4-6,8 | ER1 | 17 | 4 | [20 empty] | 3: 1; 1 4: 2; 2 5: 3; 3 6: 4
B | 29 | [IPPT], [PL], [N] | [IDEAL], [DE], [Y] | 1,4,5,8 | ER1 | 15 | 4 | [20 empty] | 1: 1; 2: 2; 3: 3; 1 4: 4
B | 30 | [ECL],[FR],[N] | [IDEAL], [DE], [Y] | 1-4,5,8 | ESR | 26 | 4 | [32 empty] | 2 | 3 | 4 | bar: 4 12
B | 31 | [ECL],[FR],[N] | [IDEAL], [DE], [Y] | 1-4,5,8 | ESR | 29 | 4 | [34 empty] | 1 | 2 | 3 | 4
A | 32 | [ECL],[FR],[N] | [IDEAL], [DE], [Y] | 1-6,8 | ER1 | 37 | 12 | [42 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
A | 33 | [LZPQ],[DE],[N] | [IDEAL], [DE], [Y] | 1,4-6,8 | ER1 | 20 | 11 | [25 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11
B | 34 | [IPPT], [PL], [N] | [CEDRAT], [FR], [Y] | 1-8 | ER2 | 26 | 1 | bar: 7
B | 35 | [IPPT], [PL], [N] | [IDEAL], [DE], [Y] | 1-8 | ER2 | 38 | 1 | [43 empty] | 1
|  | LEGEND | deleted
retained

## Gantt Chart
[12 empty] | SolMech'2012 | [5 empty] | ECL |  |  |  |  | SMART'2013 Midterm Review | [6 empty] | LZPQ | [6 empty] | IPPT |  |  |  |  | CEDRAT |  |  |  |  | SMART'2015 (Smart-Nest session) |  |  |  |  | IPPT PARIS (final meeting)
No | [Sending institution] [Country] [Commercial sector Y/N] | [Hosting/ Recruiting institution] [Country] [Commerial sector Y/N] | Type | Total PM | Year 1 2012 | [11 empty] | Year 2 2013 | [11 empty] | Year 3 2014 | [11 empty] | Year 4 2015
[5 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
[5 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48
Start
1 | [ADAPTRONICA], [PL], [Y] | [IPPT], [PL], [N] | ER2 | 10 | [12 empty] | 1 | 2 | 3 | 4 | 5 | 6 | [6 empty] | 7 | 8 | 9 | 10
2 | [ADAPTRONICA], [PL], [Y] | [ECL],[FR],[N] | ER1 | 7 | [30 empty] | 1 | 2 | 3 | [7 empty] | 4 | 5 | 6 | 7
3 | [ADAPTRONICA], [PL], [Y] | [ECL],[FR],[N] | ER2 | 8 | [32 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8
4 | [IDEAL], [DE], [Y] | [ECL],[FR],[N] | ESR | 8 | [32 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8
5 | [ADAPTRONICA], [PL], [Y] | [LZPQ],[DE],[N] | ER2 | 10 | [21 empty] | 1 | 2 | 3 | 4 | 5 | [6 empty] | 3 7 7: 6; 3 8 8: 7 | 8 | 9 | 10
6 | [IDEAL], [DE], [Y] | [LZPQ],[DE],[N] | ER1 | 9 | [19 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9
7 | [IPPT], [PL], [N] | [ADAPTRONICA], [PL], [Y] | ER2 | 16 | [12 empty] | 1 | 2 | 3 | 4 | 5 | 6 | [6 empty] | 7 | 8 | 9 | 10 | [14 empty] | 11 | 12 | 13 | 14 | 15 | 16
8 | [ECL],[FR],[N] | [ADAPTRONICA], [PL], [Y] | ESR | 8 |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8
9 | [ECL],[FR],[N] | [ADAPTRONICA], [PL], [Y] | ER1 | 4 | [16 empty] | 1 | 2 | 3 | 4
10 | [LZPQ],[DE],[N] | [ADAPTRONICA], [PL], [Y] | ESR | 9 | [33 empty] | 1 | 2 |  |  | 3 | 4 |  |  |  | 5 | 6 |  | 7 | 8 | 9
11 | [LZPQ],[DE],[N] | [ADAPTRONICA], [PL], [Y] | ER1 | 4 | [9 empty] | 2 | 3 | 4 | bar: 8
12 | [LZPQ],[DE],[N] | [ADAPTRONICA], [PL], [Y] | ESR | 4 | [44 empty] | 1 | 2 | 3 | 4
13 | [LZPQ],[DE],[N] | [ADAPTRONICA], [PL], [Y] | ER1 | 2 | [34 empty] | 1 | 2
14 | [IPPT], [PL], [N] | [CEDRAT], [FR], [Y] | ER2 | 5 | [26 empty] | 1 | 2 | 3 | 4 | 5
15 | [IPPT], [PL], [N] | [CEDRAT], [FR], [Y] | ER2 | 6 | [29 empty] | 1 | 2 | [12 empty] | 3 | 4 | 5 | 6
16 | [IPPT], [PL], [N] | [CEDRAT], [FR], [Y] | ER2 | 2 | [24 empty] | 1 | 2
17 | [IPPT], [PL], [N] | [CEDRAT], [FR], [Y] | ESR | 5 | [21 empty] | 1 | 2 | 3 | 4 | 5
18 | [IPPT], [PL], [N] | [CEDRAT], [FR], [Y] | ER2 | 2 | [24 empty] | 1 | 2
19 | [IPPT], [PL], [N] | [CEDRAT], [FR], [Y] | ER1 | 2 | [46 empty] | 1 | 2
20 | [ECL],[FR],[N] | [CEDRAT], [FR], [Y] | ER1 | 0
21 | [LZPQ],[DE],[N] | [CEDRAT], [FR], [Y] | ER1 | 4 | [21 empty] | 1 | 2 | 3 | 4
22 | [LZPQ],[DE],[N] | [CEDRAT], [FR], [Y] | ER1 | 4 | [37 empty] | 1 | 2 | 3 | 4
23 | [IPPT], [PL], [N] | [IDEAL], [DE], [Y] | ER2 | 2 | [34 empty] | 1 | 2
24 | [IPPT], [PL], [N] | [IDEAL], [DE], [Y] | ER2 | 2 | [36 empty] | 1 | 2
25 | [IPPT], [PL], [N] | [IDEAL], [DE], [Y] | ER2 | 4 | [38 empty] | 1 | 2 |  |  | 3 | 4
26 | [IPPT], [PL], [N] | [IDEAL], [DE], [Y] | ER2 | 2 | [40 empty] | 1 | 2
27 | [IPPT], [PL], [N] | [IDEAL], [DE], [Y] | ER1 | 4 | [44 empty] | 1 | 2 | 3 | 4
28 | [IPPT], [PL], [N] | [IDEAL], [DE], [Y] | ER1 | 5 | [21 empty] | 1 | 2 | 3 | 4 | 5
29 | [ECL],[FR],[N] | [IDEAL], [DE], [Y] | ESR | 4 | [30 empty] | 1 | 2 | 3 | 4
30 | [ECL],[FR],[N] | [IDEAL], [DE], [Y] | ESR | 3 | [34 empty] | 1 | 2 | 3
31 | [LZPQ],[DE],[N] | [IDEAL], [DE], [Y] | ER1 | 9 | [12 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9
164